## Checklist
Apple Squeeze | 2017-09-30 |  |  | 2022-10-01 | 2023-09-16
| Assigned to | Due | Complete | Assigned to | Assigned to | Due | Complete
Overall | Jeanne, Bob |  |  | Bob | Wendy, Bob
Determine date (based on apples) |  |  |  |  | Jerry S, Wayne, Wendy, Bob
Determine hours |  |  | done |  | Wendy, Bob. |  | We started squeezing at 9:30 and selling at 10am when the garden market opened. In 2024, lets officially open at 10.
Set Price |  |  |  | Bob | Bob |  | $10/1 gal, $8/2 or more gal, $5/half gal. Customers buy small quantities and are not price sensitive.
Get Health Department permit | Margaret |  |  | Larry Gramling 253 250 8341 | Larry Gramling 253 250 8341 |  | Start 9/1/22
Assign Team Leaders | Jeanne |  |  | Bob | Wendy
Physical Setup | Wayne |  | done | Wayne | Wayne
Bake Sale | Gina Munson |  | done | Sheryle Jaschke, 760-219-0309 | Sheryle Jaschke, 760-219-0309
Food (hot dogs, …) | Sue Huesby |  | done | Sheryle Jaschke, 760-219-0309 | Sheryle Jaschke, 760-219-0309
Cider crew | ? |  |  | Jerry | Jerry
Docents |  |  |  | Peggy Hodge | Peggy Hodge |  | Staffed farmhouse, AB, saw museum, coop2, barn.
Publicity | Lynne |  | done | Penne | Penne
Jugs |  |  |  |  | Jugs
Long Lead
Buy Jugs 1 month early |  |  |  |  | Wendy |  | Try for a plastics company. ULINE is last resort because they are expensive. In 2023 our normal supplier, Anderson Plastics, closed. We used ULINE but it cost us $1.3/jug including delivery to Bob's house in Edgewood.
Buy food
Call for bake sale
Physical Setup | Wayne | Sat 9/30 |  | Wayne | Wayne
Determine locations of events, special tables, parking |  |  |  |  | Wendy
Update map
Setup Decorations (?) |  |  |  | Didn't do any. | Didn't do any.
Put up tents, tables, chairs | Wayne | Wed 9/27 |  | Crew: Jerry, Todd, Bob Friend, Jim Battishill, Wendy Lessard | Crew: Jerry, Todd, Bob Friend, Jim Battishill, Wendy Lessard
Setup machine | Wayne |  |  | Wayne & Crew | Wayne & Crew | 3 weeks early
Setup for cider sale | Wayne | Sat 9/30 |  |  |  | 2022-10-01
Setup for Hot Dogs |  |  |  | Sheryle | Sheryle | 2022-10-01
Setup for Bake Sale |  |  |  | Sheryle | Sheryle | 2022-10-01
Cash Boxes for bake sale & cider & hotdogs | Todd | Sat 9/30 |  | Todd | Todd | 2022-10-01
Sound system set-up | n/a |  |  | n/a | n/a | n/a
Put up permit |  |  |  | Larry G | Larry G | 2022-10-01
Publicity
Sounder Article | Lynne | done | done | Penne Wilson | Penne Wilson
Newsletter article | Lynne | done | done | Penne Wilson | Penne Wilson
Post at store | Lynne |  |  | Penne Wilson | Penne Wilson
Post on Facebook | Lynne |  |  | Penne Wilson | Penne Wilson
Poster? If so, where post | Ed
Sandwich Boards week before |  |  |  | Penne Wilson | Bob, used Island Arts boards.
AI Assistant | Bob | done | done | Bob | Bob
Email |  |  |  | Peggy | Peggy
Apples
Turn on cold room |  |  |  | Wayne | Wayne | 2022-09-21
Arrange ?# volunteers | Jeanne |  |  | Jerry | Jerry
Pick apples | Wayne | Wed 9/27 |  | Jerry | Jerry
Pick apples@McGoldrick | Dick | Thur 9/28 |  | Jerry | Jerry
Pick apples @ winery
Pick apples @Andersons
Food |  |  |  | Sheryl Jaschke, 760-219-0309
Caramel for apples | Kathy Guild | done | done | Sheryl Jaschke, 760-219-0309 | Linda Simonsen
Make caramel apples | Kerry Schaffer | Fri 9/29 |  |  | Linda Simonsen
Get hot dogs and buns | Jeanne | 2017-09-26 |  | Used hot dogs from farm day. | Bob
Sell hot dogs | Sue Huesby? |  |  | Sheryle Jaschke | did for staff only | 2022-10-01
Cider
Ensure enough jugs, lids | Dick |  | in work | Dick | Wendy |  | Need to order 1-2 months early.
Labels | Mickey |  | ? | Bob | Bob
Apply labels to jugs |  |  |  | Lori M | Bob, Cori |  | 2023 Did during the squeeze
Machine crew
Selling crew | Carol Pascal |  |  | Carol, Dave Durrett | Carol, Dave Durrett, Sue
bottling crew | ? |  |  | Todd, Lori | Todd, Mike W |  | Get before and after counts of jugs to determine how much we sold.
Bake Sale | Gina Munson |  |  | Sheryle Jaschke, 760-219-0309 | Sheryle Jaschke, 760-219-0309
recruit volunteers for baking | Gina Munson |  | done | Sheryle Jaschke, 760-219-0309 | Sheryle Jaschke, 760-219-0309
recruit volunteers for staffing site |  |  |  | Sheryle Jaschke, 760-219-0309 | Sheryle Jaschke, 760-219-0309
Setup and sell | Gina Munson |  |  | Sheryle Jaschke, 760-219-0309 | Sheryle Jaschke, 760-219-0309 | 2022-10-01
Lunch for Crew | Liane, Jane G? |  |  | n/a | Bob (hotdogs)
RESULTS
Squeezed |  |  |  | 114 gallons from 40 bags. | 400 gal from 170 bags (really!)
Price |  |  |  | Half gallons $5/member, $6/nonmember | $10/gal, $8/gal for 2 or more. $5/half gal.
Sold |  |  |  | 110 gallons for $1205 (including $151 on cc). | 326 gal. $2845. ($350 on CC)
Food |  |  |  | Sold $1084. Bake sale, hot dogs, hot cider, caramel apples. | $451. Caramel apples, bake sale, hot cider. No hot dogs.

## Sold
| Bags | Produced | Sold | $/gal | Date | Cider $ | Food $
|  | Gal | Gal
2017
2018 |  | 300 | 300 | 8 |  | 2400 |  | estimated based on $2400 income.
2019 |  | 212 | 212 | 8 |  | 1700 |  | estimated based on $1700 income.
2020 |  | 150 | 150 | 8 | 2020-10-07 | 1212 |  | estimated based on income
2021 |  | 300 | 300 | 8m/10nm | 2021-09-27 | 2490 |  | In 2021: Sold 250 gal + 50 gal leftover and gradually sold.
2022 | 40 | 114 | 110 | 10m/12nm, only sold 1/2 gallons | 2022-10-01 | 1205 | 1084 | Low yield year, only sold 1/2 gal containers for $5members, $6non-members
2023 | 170 | 400 | 326 | 10/1, 8/2 or more | 2023-09-17 | 2845 | 451 | $4429 including plants and garden market
Note on H8: Bake sale, hot cider, caramel apples, hot dogs