## Checklist
Holiday Open House | 2021-12-05
| Assigned to | Due | Complete | Notes
Overall
Determine hours | AIHS Board |  | done | 1pm - 3pm
Determine venue (AB or Farmhouse) | AIHS Board
Get Health Department permit | Not needed
Assign Team Leaders | Lora |  |  | Assign several weeks in advance
Physical Setup | Jon |  | done | Inside the AB. A few tables and chairs.
AB inside decorations | Beula Robb |  | done | To be done ahead of the event
AB outside lights | Ed, Jeanne |  |  | Also Simonsens helped
Farmhouse decorations | Karen S
Cookies | Lora |  | done | Bought from Delish Bakery because of COVID concerns. Normally baked by island residents.
Lefse (cookies) |  |  |  | Previously led by Lynne Jacobsen, who held a Lefse baking session with islanders on the day before the open house.
Drinks: Cider & Coffee | Karen S
Publicity | Penne |  | done | See event publicity checklist
Music | Rick A |  |  | Has been Rick A and Rick Stockstad. Needs electric keyboard.
Physical Setup on day of event
Setup tables and chairs | Jon
Setup food (cookies) & Drinks | Karen S
Turn on Air Handler | Jon
Setup for music. | Rick S
Put out OPEN signs and flag. | Jon
Publicity
Sounder Article | Penne | done | done
Newsletter article | Penne | done | done
Post at store | Penne
Post on Facebook | Penne |  |  | 3 pages: AIHS;AI Community; Meanwhile on AI
Email to all members | Penne, Bob
Sandwich Boards week before | Penne, Bob
AI Assistant | Bob | done | done
Food
Coordinate cookies. | Lora
Cleanup
Cleanup and lockup | Jon
Take down AB inside decorations | Beula
Take down farmhouse inside decorations | Karen
Take down outside lights | Ed, Jeanne